Stars and Stripes Golf AGENDA – (Date)

10:30 – 11:30 	Sponsor & Facilities Set Up	At the Holes and Clubhouse

11:30 – 12:30 	Golfer Check In/Registration	At Clubhouse, Sandwiches and Drinks

12:30 – 1:00		Golfers “Mount Up” 			To carts, Announcements, Anthem

1:00	 			Shotgun Start				Golfers Tee Off at Designated Holes

5:00 – 8:00      Dinner, Raffle, Trophies		Sponsor Remarks & Trophy Presentation

Stars and Stripes Golf Timelines

EVENT TIMELINE

- By 90 Days Out

  - Secure location and Date

  - Decide on Sponsorship Levels and Charge

  - National to Produce Sponsorship and Golfer Promo Flyer

  - Designate site to hold Raffle and Auction Items

  - Begin to promote for Golfers and Sponsors

- By 60 Days Out

  - Register Hole In One Insurance Policy (Hole In One International)

  - Book Anthem singer and Color Guard

  - PA system or DJ for Event/Banquet

- By 30 Days Out

  - Order Trophies

  - Order Goodie Bags

- By 15 Days Out

  - Remind Sponsors to drop off sponsor goodies

  - Order Sponsor Signage for Holes and Title Sponsor Banner

  - Finalize Dinner Menu

  - Pre-Order Lunch

- Week of the Event

  - Set date to stuff goodie bag

  - Designate responsibilities for staff at event

    - 2 Registration Clerks

    - 2 For extras sales (Raffle tickets, String Pulls, Mulligans…)

    - 1 Designated Spotter for Hole in One

    - 2 Escort sponsors to holes

Stars and Stripes Golf Checklist

EVENT CHECKLIST

- Registration List

- Registration Forms (On-Site Registration)

- PayPal Triangle and Smart device set up for on-site credit payments

- Signage (banners, hole signs, hole in one, VAREP banner and pop-ups)

- Registration tables and chairs (VAREP table cloths)

- Stuffed Goodie Bags

- All raffle and auction items

- Raffle Tickets

- String Pull Box

- Trophies

- Duct tape, Sharpie, Pens

Stars and Stripes Golf SPONSORSHIP INFORMATION

Dinner Banquet $2,500

Drink Cart Sponsor $1,500

Lunch “Brown Bag” Sponsor $1,500

Hole-In-One $750

Closest to the Pin $500

Longest Drive $500

15 Hole Sponsors $250 each

Optional Sponsorships

- $1,500 – Golf Shirt, Golf Towel, Glove, or Balls (With Sponsor Logo)

Raffle and Extras

- Raffle Tickets $5 each (or) 5 for $20

- String Pulls $5 per pull

Sponsor Benefits

POST TOURNAMENT BANQUET SPONSOR - $2,500 - 1 AVAILABLE

Receive four (4) player tickets for the tournament, recognition and branding opportunity, provide company literature distributed to players in Goodie Bag, and speaking opportunity at Post Tournament Awards Banquet.

BEVERAGE CART SPONSOR - $1,500 - 1 AVAILABLE

Receive two (2) player tickets for the tournament, logo on beverage cart, provide company literature distributed to players in Goodie Bag, speaking opportunity at opening announcements.

BROWN BAG LUNCH SPONSOR - $1,500 - 1 AVAILABLE

Receive two (2) player tickets for the tournament, Lunch provided to each Golfer on their cart, company branding on brown bag (sponsor to provide sticker), provide company literature distributed to players in Goodie Bag, and speaking opportunity at opening announcements.

HOLE-IN-ONE SPONSOR - $750 - 1 AVAILABLE

Booth at designated hole and display of prize, one yard sign, provide company literature distributed to players in Goodie Bag, acknowledgement at Post Tournament Awards Banquet for designated trophy.

CLOSEST TO THE PIN SPONSOR - $500 - 1 AVAILABLE

Booth at designated hole and display of prize, one yard sign, provide company literature distributed to players in Goodie Bag, acknowledgement at Post Tournament Awards Banquet for designated trophy.

LONGEST DRIVE SPONSOR - $500 - 1 AVAILABLE

Booth at designated hole and display of prize, one yard sign, provide company literature distributed to players in Goodie Bag, acknowledgement at Post Tournament Awards Banquet for designated trophy.

HOLE SPONSOR(S) - $250 – 15 AVAILABLE

Booth at designated hole, one yard sign, provide company literature distributed to players in Goodie Bag.

DONATION / SILENT AUCTION / RAFFLE GIVEAWAYS

We are looking for new desirable items (do not have to be golf or sports related), such as autographed photographs or other memorabilia, artwork, crafts, Tablets, timeshare week, a boat excursion, massages, tickets to Sporting Events, Starbucks gift cards, Home Depot gift cards, etc., all suitable for our Silent Auction and Raffle to be held during the Post Tournament Awards Banquet.  Any baskets or donations can be arranged to be picked up or you can drop off day of event.